REAL CHEMISTRY / INTERNAL DISCUSSION

# Inflection Radar

Executive decision brief for an eight-week emerging neuropsychiatry opportunity-intelligence pilot

| Prepared for | Prepared by | Version |
| --- | --- | --- |
| Will Hargreaves / Real Chemistry | Rayven-Nikkita Collins | 28 July 2026 · v2.0 |

The public evidence establishes what Real Chemistry already demonstrates. It does not resolve what only Real Chemistry can know. Pilot 1 is designed around that boundary.

# The decision on the table

Approve the scope and minimal inputs for Pilot 1. No production integration, internal data, CRM connection, licensed Real Chemistry database, or ANATOMI build is required.

| DECISION REQUESTED | Proceed with a 50–75-company public-source research universe and a 12–15-account human-reviewed priority portfolio. |
| --- | --- |

## What approval does not include

A production AI product or autonomous target-selection system.

Use of client-confidential, patient-level, licensed-restricted, or internal Real Chemistry data.

ANATOMI, CRM, or production engineering integration.

A claim that Real Chemistry lacks AI, analytics, intelligence, monitoring, or growth capability.

## The precise candidate white space

Real Chemistry publicly demonstrates nearly all technical and analytical ingredients. What is not publicly demonstrated is a unified, owned growth workflow that organizes early external company evidence around prospective-account decisions.

# Will’s diligence questions: direct answers

| Question | Answer |
| --- | --- |
| AI model | A governed model-task portfolio, not one model for every task. AI may assist bounded extraction, comparison, classification, contradiction detection, and draft synthesis. Humans retain consequential authority. |
| Assumptions | Every material assumption is registered and labeled evidence-supported, methodological, provisional, or internal-calibration-required. |
| Sources and permissions | Pilot 1 defaults to official, first-party, public-domain, and properly permitted sources. Rights and restrictions travel with every record and derived output. |
| Compliance | Company-level research; no PHI. Restricted sources are excluded by default. Human gates, audit records, and escalation pathways preserve healthcare, privacy, security, and AI-governance boundaries. |
| Reliability and limits | Facts, findings, inferences, and hypotheses remain distinct. Public evidence can support review priority; it cannot establish clients, conflicts, relationships, economics, capacity, or pursuit history. |

# What Pilot 1 produces

| Scale | Outputs | Boundary |
| --- | --- | --- |
| 8 weeks | Company universe; 12–15 priority dossiers; external opportunity score; rejected/deferred list; recommendation. | No production integration. |
| 50–75 companies | Source-permission, assumption, evidence, and model-task registers. | No internal or client-confidential data. |
| Human-reviewed portfolio | Advance, monitor, defer, exclude, redirect, or insufficient-evidence dispositions. | No automated pursuit decision. |

| EXTERNAL QUESTION | Which companies appear externally attractive for Real Chemistry review? |
| --- | --- |

| INTERNAL QUESTION | Which externally attractive companies are plausible internal pursuits? |
| --- | --- |

# Three-stage progression

| Stage | RN builds | Real Chemistry contributes | Decision |
| --- | --- | --- | --- |
| Discover / Pilot 1 | Universe, ontology, evidence architecture, external score, dossiers, registers. | Scope, geography, stage, reader, public priorities, success standard. | Which companies warrant review? |
| Qualify / conditional | Internal viability layer and calibrated review workflow. | Clients, pursuits, conflicts, ownership, thresholds, economics, judgment. | Which are plausible pursuits? |
| Institutionalize / conditional | Monitoring, queues, outcome capture, recalibration design. | Approved systems, CRM, data feeds, ownership decisions. | Should this become persistent? |

## Eight-week cadence

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Scope | Taxonomy | Universe | Verify | Score | Dossiers | Portfolio | Handoff |

# Safeguards and evaluation

Five human gates: source approval, record validation, analytical approval, account review, and distribution approval.

Four evidence tiers: verified fact, corroborated finding, analytical inference, and hypothesis or early signal.

Score sensitivity, missing-data review, contradiction review, staleness checks, baseline comparison, and false-positive analysis.

Success means a defensible and useful internal review portfolio—not a promise that every ranked company becomes an account.

# What RN needs from Will now

| Input | Why it matters |
| --- | --- |
| Scope | Defines the therapeutic and company universe. |
| Intended reader | Determines depth, language, and format. |
| Public service priorities | Constrains capability mapping without relying on internal data. |
| Success standard | Defines what a useful portfolio must enable. |

| DECISION | Approve Discover/Pilot 1 first. Reserve internal calibration, ANATOMI, CRM, licensed-source enrichment, and production integration for a later decision. |
| --- | --- |